## Slide 1
Steve Kropp, Tod Schwingel and Jason Hamer
Navigating Construction Pitfalls and Tips
August 28, 2024

## Slide 2: Agenda
Willie Downs Villas
The problems
The Budget
Studies needed
Change Orders
Builder’s Risk Insurance
Davis Bacon
Pitfalls and delays
Finally, the Finish line
Other Projects (Identify the issue)

## Slide 3: Background
The Development was preliminarily awarded $4,531,000 in HOME funds for the construction 50 new units located in Highlands County. SMG submitted a negative recommendation in the final Credit Underwriting Report (“CUR”). With agreement from FHFC Staff, the negative recommendation was presented to the FHFC Board at the December 8, 2017 meeting. Despite the negative recommendation, the FHFC Board approved a HOME Loan in the amount of $4,531,000 for the Development was approved at the December Board Meeting. The Borrower closed on a First Mortgage with First Bank in the amount of $1,146,250, and the FHFC HOME loan on August 8, 2018.
Following the closing of Willie Downs, progress proceeded on a normal schedule throughout 2019, with Florida Housing receiving regular construction draw requests. However, in 2020, a slowdown in draw requests occurred, with only one submitted in 2020 and one in 2021. Initially, this slowdown was attributed to the COVID‐19 pandemic, which significantly impacted the timely completion of construction projects. Since 2021, there was been minimal reported progress on the Development, with a construction inspection indicating construction was 96% complete. In 2023, an inspection conducted by Moran estimated Willie Downs was approximately 87% complete. The reduction in construction completion is partially due to the Development remaining unfinished and unoccupied for several months. Consequently, HCHAI officially terminated the construction contract with GHD Construction Services, Inc. (“GHD”) due to default on August 12, 2022, and requested Frankenmuth Mutual Insurance Company, under their Performance Bond, to assume responsibility. Frankenmuth Mutual Insurance Company responded on December 21, 2022, advising that to mitigate costs, HCHAI should proceed with completing GHD's contract.

## Slide 4: According to the Contract
• The site underground utilities are complete (storm, sanitary, domestic water and fire sprinkler)
• The roadway asphalt is complete and striped
• The grading around the buildings is complete and sod is installed at the site islands at the clubhouse and Buildings # 2 -13
• The water is still not connected to the buildings, but the service lines to the buildings are in place
• Both dumpster slabs, walls, gates and bollards are in place and stucco is applied and painted
• The sanitary is connected to the buildings
• The rear entry slabs are in place at all Buildings and the Clubhouse
• The bushes at the front of each Building are complete and mulch is placed
• The island plants and mulch are in place
• The excavation of the rear retention area is complete
• The sidewalks from Building # 1 to 13 appear to be complete
• The local water service to the backflow preventer is in place
• The on-site electrical service by the utility company is in place
• The electric company is still installing the electrical meters
• Century link cable is installed

## Slide 5: Willie Downs Ariel Photo

## Slide 6: Willie Downs Before

## Slide 7: Willie Downs Before

## Slide 8: Willie Downs Before

## Slide 9: Willie Downs Before

## Slide 10: Willie Downs Before

## Slide 11: Willie Downs Before

## Slide 12: Willie Downs Before

## Slide 13: Willie Downs Before

## Slide 14: Willie Downs Before

## Slide 15: To much slope

## Slide 16: To much slope

## Slide 17: Sloping Sidewalks

## Slide 18: Remove Trees from retention areas

## Slide 19: Sources
Sources | Total Loan | Amount Funded | Availble
First Bank of Clewiston | $ 1,146,250 | $ 907,183 | $ 239,066.68
FHFC HOME | $ 4,531,000 | $ 3,625,492 | $ 905,508.24
Highlands County SHIP | $ 115,900 | $ 41,000 | $ 74,900.00
New FHFC HOME loan | $ 2,050,000 | $ - | $ 2,050,000.00
Total Sources | $ 7,843,150 | $ 4,573,675 | $ 3,269,474.92

## Slide 20: Change Orders
Change Order | Amount
Change Order 1 builder’s risk | $ 14,666.50
Change Order 2 appliances | $ 14,284.90
Change Order 3 range hoods | $ 5,000.00
Change Order 4 plumbing | $ 15,950.00
Change Order 5 mold | $ 17,348.00
Change Oder 6 deduct on CO2 | $ (3,851.10)
Change Order 7 Site work | $ 847,935.00
Change Order 8 Concrete | $ 192,570.00
Change Order 9 irrigation and landscaping | $ 159,196.00
Change Order 10 deduct orginal items for site | $ (186,800.00)
Change Order 11 additional tile work | $ 39,039.00
Change Order 12 builder’s risk | $ 18,007.50
Change Order 13 deduct for tile | $ (2,035.00)
Change Order 14 Hickey Changes | $ 32,450.00
Change Order 15 plumbing | $ 10,505.00
Change Order 16 Builders Risk | $ 41,777.25

## Slide 21: Additional Site Work needed
Additional Site Work | 
Mobilization | 25,000
Survey | 15,000
Testing | 9,500
Mill asphalt | 15,000
25 loads of Millings hauled away | 5,000
Clear and Grub | 126,500
Cut/Fill | 25,000
Export 50 loads at $200 per load | 10,000
Final Grade | 10,000
Water Lines | 298,900
Test Sewer | 7,500
Roadwork | 203,200
1,320 syd overlay | 19,800
Remove 2,000 sft of concrete | 6,000
Concrete Flume | 2,500
Fix drain structures | 10,000
Irrigation and Landscaping | 148,130
Install new sidewalks | 192,570
FHC fee | 35,000
Contractor profit | 70,000
Total Site work additions | 1,234,600
Existing funding | 386,253
Additional Costs | 848,347
Contingency | -
Total additional costs | 848,347

## Slide 22: Sidewalks removed

## Slide 23: TEAR IT OUT

## Slide 24: Removing the paving and adding water pipes

## Slide 25: Laying down the proper base

## Slide 26: Big Pipe into little Pipe

## Slide 27: When the Tropical Storm hit

## Slide 28: See if you can identify the issue in the following pictures:
Each picture has a problem
What is it?

## Slide 29: Identify the Problem Front door openings are not installed correctly

## Slide 30: Identify the problem wire mesh not embedded in slab properly

## Slide 31: Identify The problem Garage door lintels not installed level. CMU block higher at one site compared to other side

## Slide 32: Did they follow the plan Slab at front porch to jog per plans

## Slide 33: What is the issue?

## Slide 34: The End
Questions